## Slide 1: 533 Review
Linda Laird

## Slide 2: Define a Metric
Your team is responsible for measuring complexity for your project. Define your complexity metric and present it to the class…as if the class were your boss

## Slide 3: Grading Rubric
Is GQMM used?
Is the Meta Model used? (Concept, Definition, Operational Definition, Real World Measurement)
Are the 4 D’s used?
  Decide on meaningful metrics
    Is it Valid? [Content, Construct, Criterion (Predictive capability)]
  Draw a picture—and make it eloquent
    Define it
    Set the objective
    Provide current Status
    Trend it
    Provide Benchmark, if appropriate
  Dashboard - NA
  Drilldown -NA

## Slide 4: Variability and Central Tendency
Determine the measures of variability and central tendencies for {0,5,22,6}

## Slide 5: Rubric
Variability
  Range
  Deviations
  Variance =
  SD = sqrt(sum (deviations2/N*))
  Index of Variance
Central Tendency
  Mean
  Median
  Mode
* - for a full population

## Slide 6: Gearing Factors
If you have 30M LOC, how many FPs?
  Do it for C and C++
Given these numbers, what would be the estimated effort?

## Slide 7: Cyclomatic Complexity
This code determines all prime numbers less than n. What is the McCabe
Cyclomatic Complexity for the pseudocode below. Use the basic definition of CC.
Eratosthenes(n) {
a[1] := 0
for i := 2 to n do a[i] := 1
p := 2
while p2 < n do {
j := p2
while (j < n) do {
a[j] := 0
j := j+p
}
repeat p := p+1 until a[p] = 1
}
return(a)
}

## Slide 8: CC Answer
For Cyclomatic complexity, the easiest way it to count the number of binary decisions.
There are 4. Therefore, CC = BD + 1 = 4+1 = 5

## Slide 9: IFC Complexity
What is the information flow count (IFC) using the IEEE standard for the Sieve of Eratosthenes? Assume that the number of flows in = 1.
Eratosthenes(n) {
a[1] := 0
for i := 2 to n do a[i] := 1
p := 2
while p2 < n do {
j := p2
while (j < n) do {
a[j] := 0
j := j+p
}
repeat p := p+1 until a[p] = 1
}
return(a)
}

## Slide 10: IFC answer
IEEE definitions:
IFC = (fanin * fanout) ^2
fanin = local flows into a procedure + number of data structures from which the procedure retrieves data
fanout = local flows from a procedure + number of data structures that the procedure updates
Local Flows in = 1
Number of Data Structures In = 1
# of Flows out - 0
Number of Data STructures Out = 1
Fan-In = 2 Fan-Out = 1.
IFC=(fan-in*fanout)2
IFC =4
I can agree that the flow out is the return as well, in which case it = 16.

## Slide 11: Estimation Problems
If you were building a new OO system, with a sophisticated UI,
and you know you have 25 use cases and 10 key classes and 5 actors,
and assuming: 1) Efactor = 10, Tfactor = 40 and all the factors are estimated to be of average weight/complexity
Using Lorenzo/Kidd
a. What do you estimate the total number of classes to be?
b. Using effort as a function of use cases, what do you estimate
the work effort to be?
Using Use Case Points,
what do you estimate the work effort to be?
Considering these different numbers, what do you estimate the
work effort to be? Why?

## Slide 12: Estimation Answers
System: A sophisticated UI, 25 use cases, 10 key classes and 5 actors, and assuming: 1) Efactor = 10, Tfactor = 40 and all the factors are estimated to be of average weight/complexity
A ) # = support classes = 3 * number of key classes (GUI) = 30; number of total classes = 40 (use a multiplier of 3 rather than 2.5 because of complex UI)
b) Estimate 1 stf month per use case => 25 staff months
Mean = 32.5, SD = 7.5 for LK
For UCPs, have 25 use cases and 5 actors, all of average complexity.
25 Use Cases of Aver Complexity = 10*25 = 250 UAW
5 actors = 5*2 = 10 UAW
UUCP = 260
Tfactor = 40 then TCF = 1
Efactor = 10 then EF = 1.1
So UCP = 260*1.1= 286
At 160 hours per staff month and 20 hours per UUCP = 286*20/160 = 35.7 staff months.
So -- want to take mean and sd for 35.7 and 32.5.
Mean = 34.15, SD = 1.3 Staff months

## Slide 13: Reasonable?
You need an estimate for a new system that your team needs to build. It has 3 use cases, each with 15 transactions and 3 on-line interfaces to different systems. You ask one of the people who works for you to estimate it. They come back with 6 staff months. Is this reasonable or not? Please show your work.

## Slide 14: Answer
3*15 + 3*2 = 51 UUCPs.
20 hours per UCP means 2 UCPs per week.
so we have ~ 25 staff weeks if the adjustment factors are all 1. So assuming that nothing is unusual about this project (e.g., 20 is reasonable, and so EF and TF both are ~ 1) then 6 months is actually a very good estimate.

## Slide 15: T or F
Tools give you the most accurate results for estimation. Use them. (T/F)
Using experienced developers to estimate projects is the best way to get good estimates. (T/F)
2.5 Defects Delivered per KLOC is reasonable for code which fires missiles (T/F)

## Slide 16: You are the development manager and your team …
comes up an estimate of 8 months duration with 6 people full time, and you know that the job needs to be done in 6 months. You find out that your team used estimation formulaes based on basic cocomo equations -- and assumed organic mode.
1) How many lines of code did they initial estimate?
2) You know they intend to write the project in Java. How many function points did they predict?
3) You know you can reduce the functionality to cut the schedule by working with the customer. How many function points do you have reduce to have the estimate come out to 6 months instead of 8?
Remember -- if A = X^C then ln(A) = ln (X^C) = C* ln (X). and if a = ln(b), then e^a = b
Use Staff Months = Duration * Number of People
Use 53 LOC per FP for Java

## Slide 17: Bring it in on schedule
1) The number of staff months = 6*8 = 48
48=2.4*x^1.05;
ln (x) = ln(48/2.4) / 1.05;
x = exp (2.853);
x= 17.34 so 17.34KLOC
2)17.34K/53=327 function point
3) 36=2.4*y^1.05, y=exp(ln(36/2.4)/1.05), y = 13.1K LOC, # FPs = 248; need to reduce 327-248 FPs = 79 FPs

## Slide 18: Defect Removal
Week 1 2 3 4 5 6 7
defects found 2 4 6 5 7 4 6
CUM defects 2 6 12 17 24 28 34
above is the arrival data for defects.
predict, using one method only, the total number of defects remaining in the product.
what is the total DRE so far?

## Slide 19
Can't predict total. Can't predict DRE. No convergence yet.

## Slide 20: Predicting TRs
You have a small project (10 K) that has the turnover schedule shown below.
You expect TRs to appear at the rate of
30% 1 week after turnover
40% 2 weeks after turnover, and
30% 3 weeks after turnover.
You expect to find 10 TRs per KLOC during the entire testing turnover period (e.g., thru week 8). How many TRs do you predict to appear week 4?
Week 1 2 3 4 5 6
Turnover (KLOC) 0 1 3 4 2 0

## Slide 21: TRs
# of TRs =(0*.3 + 1*.4 + 3* .3)*10 = 13

## Slide 22: DRE
What is DRE
What is a reasonable DRE for System Test?
  If you don’t know, how would you find out?

## Slide 23: DRE
DRE is defect removal efficiency
DRE for ST
  ~30 to 40% for each testing activity
Could look at Coqualmo, at other models, at other projects

## Slide 24: Process Metrics
Why do we need in-process metrics?
Are they more valuable in large developments or small?
In agile developments or in waterfall developments?

## Slide 25: In-process metrics
So we can tell where we are – especially in the long interval phases
Large
Waterfall

## Slide 26: Reliability
If over 100 days
  the reliability of your network is 99%
  The reliability of your software is 99.5%
  The reliability of your hardware is 99.8%
What is your expected failure rate? Assume an exponential distribution.
Notes: Prob of success = .88&

## Slide 27: Reliability Answer
Reliability = Probability of all being up for all 100 days = R(n)*R(sw)*R(hw)
Therefore R(100)=.983
Since R(t) = e^ (lambda*t)
  .983 = e^(-lambda*100)
  Ln(.983) = - lambda*100
  .0017/100 = lambda
  Lambda = .000017
Failure rate = .000017 failures per day