## Slide 1: Software Engineering 533: Software Metrics and Economics
Linda M. Laird
In Process Metrics & Benchmarking Lecture
Stevens Institute of Technology

## Slide 2
What is the GPS for Software Development?

## Slide 3: Agenda
In-process metrics
  Milestones
  Defects
  Code Integration
  Test Progress
Benchmarking
Homework
Project

## Slide 4
How would you measure the progress?
How do you measure the progress?

## Slide 5: In-Process Metrics
Give you a variety of ways to tell where you are
Most important is to have a project plan with measurable milestones which is tracked and reviewed (and action taken) frequently …

## Slide 6
Notes: Note that these are activities…and that you need to be able
To determine unequivocally when they are complete…so you can’t fool yourself or anyone else.

## Slide 7: And what are real milestones?

## Slide 8: Need Measurable Milestones
SMART Objectives/Milestones
  Specific
  Measurable
  Achievable
  Relevant
  Time Based
Dependent on Development Methodology

## Slide 9: Exercise: Are these SMART milestones?
Draft requirements available for review – 6/1
Internal requirement review held for development/testing – 6/8
Requirements updated and delivered to customer for concurrence – 6/15
Customer concurrence obtained – 6/25
Final requirements published and put under formal change control – 6/30

## Slide 10: Are these SMART?
Specific: We could add to each milestone the owner to increase the specificity of that milestone.
Measurable: Each one has a measurable event associated with it. In other words, it will be clear whether or not the draft is published, the review meeting held, etc.
Achievable: If we have based our intervals on like-project history, previous projects with this customer, a clear understanding of resource allocation, etc., then we can view these milestones as achievable.
Relevant: The clear understanding of what we’re agreeing to build by both the internal team and the customer is absolutely critical to achieving successful project delivery and ultimate customer satisfaction.
Time based: We have defined an actual date for each milestone.

## Slide 11: Milestones with Development Schedules
Frequently use “gate-based” process – specific points, with specific criteria/goals that you must achieve to move forward.
Examples:
  Business Cases reviewed and approved
  Code Reviews passed for all critical code
  Etc.
Frequently have 4 to 8 Gates in a project
  What might you think they are?
    Gate for OK for shipment?
    Gate for Ok to start development?

## Slide 12: Frequency of Milestones?
Dependent upon maturity of team/individual
Typically Monthly  Weekly
Default: Every 2 weeks
Issues are primarily in development & testing – what can you see and schedule?
  Tend to be longest intervals
  Needs the most attention

## Slide 13: Reporting of Progress
Typically have at least 3 different views
  Plan View – what was committed
  CWV – Current working view
  Actual – What was achieved (sometimes included with CWV once completed)
Concept of “Negative Slack” -e.g., 3 weeks behind schedule
  Allows project members to truthfully report where they are without announcing a slip
  Important for project managers who want to really know where things are

## Slide 14: Development -> Cutover In-Process Metrics
Need Techniques for Measuring Progress and Quality in Integration and Testing
  Frequently use percents – ala Planning tools
    E.g, coding is 40% complete, etc.
    Severe limitations – very easy to deceive oneself and give an incorrect evaluation (e.g., 90% done for 50% of the time).
  Instead, base measurement on what we can see and observe
Realize that there are patterns and trends, and look for them
Not Recommended
Recommended

## Slide 15: What can we see and observe?
Defects Found
Lines of Code Produced/Integrated
Tests Executed and Passed
Reviews held
?
These are the kind of measurable milestones which work…and are difficult to fool yourself that you are further along than you really are

## Slide 16: What are the patterns for arrival rates for defects?
Rayleigh Curves

## Slide 17: Raleigh Curves for Defects vs. Time
I0 I1 I2 UT CT ST GA
Phases (IBM)
  IO – High-level Design
  I1 – Low-level Design
  I2 – Code
UT – Unit Test
CT – Component Test
ST – System Test
Defects
Found

## Slide 18: Raleigh Curves for Defects - Improvements
I0 I1 I2 UT CT ST GA
For each new release or project, want to push curves to left (earlier detection) and down (fewer faults)
Nominal
Earlier
Fewer
Both
Phases (IBM)
  IO – High-level Design
  I1 – Low-level Design
  I2 – Code
UT – Unit Test
CT – Component Test
ST – System Test
Defects
Found

## Slide 19: But what do these curves really mean?
I0 I1 I2 UT CT ST GA
Phases (IBM)
  IO – High-level Design
  I1 – Low-level Design
  I2 – Code
UT – Unit Test
CT – Component Test
ST – System Test
Defects
Found
Historical

## Slide 20: ????
If lots of early defects found
  Possibilities:
    Great defect removal processes
    Buggy software
If few defects found
  Possibilities:
    Great software
    Ineffective Testing
Need additional information

## Slide 21: Quality of Process Indicator Metrics
Quality of Process Metrics – Generic Technique
  Looking at Effort vs. Outcome
For this case, look at Inspection Process. we want to know
  How good were the inspections?
  How to compare with defect rates
Used to help make the decision if defect rates  good or  bad.

## Slide 22: Example 1:
Assume that product 1 represents the typical defect rate, we are building product 2, and we find a higher than average defect rate
Trouble
And, we determine that the inspection effectiveness/effort was low…what does this indicate?

## Slide 23: Example 1: Possibility 2
Assume that we find a higher than average defect rate
It could
be good.....
And, we determine that the inspection effectiveness/effort was high…what does this indicate?

## Slide 24: And if the # of defects are the same…?
Which do you prefer?
Defects found earlier cost less to fix…Prefer Red Columns

## Slide 25: Example 2:
Assume that we are finding a lower than average defect rate …. and, we determine that the inspection effectiveness/effort was high…what does this indicate?
    We may have a good release
  Or we may just have a lot of defects in total….

## Slide 26: Quality of Process Metrics
  Important in evaluating and understanding in-process metrics
  Uses observable events

## Slide 27
Coding Progress
  How might you measure the progress?
  Remember – we want observable events…

## Slide 28: Depends on Methodology
If you are using agile methods, with monthly turnovers
  The turnovers may be good enough….with the on-going discussions
If you are using a waterfall methodology…
  You may be entering a long period where you need intermediate milestones and a understanding of progress

## Slide 29: Metrics we will Look at
Code Integration Patterns
Trouble Report
  Arrival, Closure, Backlog
Both of these are trying to measure development progress

## Slide 30: Code Integration Patterns
Goal: Know where you are in the coding process
Question: How much has been accomplished?
Metric Used: KLOC of lines turned over to integration…called code integration metric
  Other terminology for “turned over to integration” is: “under formal change control” or “integrated into libraries”
  It is the point at which formal change requests (trouble reports) are now required to update the code
  Note: Again – this is an observable event…
Empirically we’ve seen – there is a pattern of KLOC turned over in a release

## Slide 31: Code Integration Patterns
Typical s-curve code integration patterns for organizations – KLOC is the # K Lines of code integrated (or under change control, or whatever you call it.) Cum is for cumulative.

## Slide 32: Organizational Patterns
Organizations and Projects have patterns of successful (and unsuccessful) code integrations…will vary with organization and with methodologies
KLOC
Integrated
Time
Start System Test

## Slide 33: Code Integration Patterns
Simple concept:
  Understand the successful (and unsuccessful) curves of your organization’s code integration patterns
  Plan this release’s code integration
  Plot this release’s plan vs. previous release’s plans (both successful and unsuccessful)
    Look for any anomalies
  As you code, track this release’s plan vs. actuals
    Look for Problems
This is a “Quantitative, Early Warning” Indicator on the development schedule.
Team’s can have own heuristics of “upper limits” and “lower limits” for successful projects
Easy to Implement and Track

## Slide 34: Let’s compare 2 S-curves for code integration

## Slide 35: Which curve do you like better?
Project 1 (blue) has less risk because code integrated earlier

## Slide 36: Code Integration Metric
The code integration metric is a SMART metric we can use to tell where we are within the coding phase.
It is useful
  in planning to compare with other projects to see if plan is reasonable
  in execution stage to compare with “actuals” (e.g., what is actually happening) and get early warnings if schedule is at risk

## Slide 37
Coding Progress
  How might you measure the progress?
  Remember – we want observable events…

## Slide 38: Another Development Progress Indicator
Trouble Report (aka PTRS, MRs, CRs etc.) Patterns
  Faults tracked in the trouble tracking system
    Tends to be after integration
  Subset of defects/faults

## Slide 39: Why are trouble reports important?
Can impact schedule significantly
  Either +/-
Early indicator of quality
Indirect indicator of testing (& quality) progress
?

## Slide 40: What is interesting about TRs?
Arrival Rates
Departure Rates
Severities

## Slide 41: TR Arrival Rate
Can build off integration/turnover plan, assuming
  Predict # TRs per KLOC
  Arrival distribution
Overall total can be estimated from historical data, FPs, etc.
Arrival Distribution
  may follow a reliability growth pattern – typically, if one large turnover to a testing organization
  may want a custom model If incremental development,
  can start off with simple model and add more refinements.

## Slide 42: Arrival rate of TRs, cont.
Concept – that there is a typical arrival rate of TRs once a unit of code is under change control – can think of it as a function TRA(t).
Can be a variety of shapes: based on testing methodologies, etc.
Examples of shapes of curves
TRs per KLOC
Time

## Slide 43: Trouble Report Arrival Model
You can create a TR arrival Model just like you had a code integration model
Coding
Turned Over Code
TR Arrival
Model
Trouble Reports

## Slide 44: How to create a Trouble Report Arrival Plan
Determine Code Integration Plan
Using your TRA(t) and the new/changed KLOC per turnover, determine expected number of TRs over time.
Update when integration plan changes
Track plan vs. actuals

## Slide 45: Example
Assume historically, TRs = 1 per KLOC
Assume distribution of discovery (use historical data to predict)
  30% in 1st week after turnover
  35% in 2nd week
  20% in 3rd
  10% in 4th
  5% in 5th
Assume the following KLOC turned over by week
  0,0,0,0,0,10,20,10,0,25,30,90,20,10,5,3
Then what would be the Expected TR arrivals?

## Slide 46: Sample Integration and TR Arrival Plan

## Slide 47: Class Exercise
Assume your project has 100KLOC. You will turn it over in 3 builds, on Jan. 1st, Feb 1st, and March 1st.
Your development team tells you that they are turning over 20% of the code in build 1, then 30%, then 50%.
What is your code integration plan by # of KLOC?
Historically, once the code is turned over, you find defects at the rate of 30% the first month, then 40% each the next 2 months. You have predicted an inserted defect density of 10 per KLOC.
What is your expected TR arrival curve?

## Slide 48: Use of Arrival Patterns
Compare against actuals*
Compare against other projects
Update as Integration Plan changes
If TRs are arriving faster or slower than plan
  Determine why Using Effort/Outcome Indicator Model
* “actuals” means what actually happens

## Slide 49
TR Backlog Models
  TR Backlog is
    The number of TR that haven’t been fixed yet
    This can build up to large numbers on big projects (e.g., in the hundreds or thousands)
  Issue: Trying to predict when the backlog of “unfixed” TRs will be low enough to ship

## Slide 50: Trouble Report Process Model
You can create a TR backlog model just like you had a code integration and TR arrival model
Coding
Turned Over Code
TR Arrival
Model
Open Trouble Reports
TR Backlog
Model
Closed Trouble Reports

## Slide 51: TR Backlog Model
Testing
Trouble Reports
Debugging
Back-
log
Fixed Trouble Reports

## Slide 52: TR Backlog Models
Consider
  Historical Rates of closure
  Arrival rates
Can create simpler model based upon typical closure rates
  May not be as highly predictive, but easier and useful.
Can develop more complex models based upon testing schedules
  More difficult
  Only for the final part of the development/testing process

## Slide 53: Example: Backlog Model
Objective: Come up with a model for number of TRs in backlog.
  Use Code Integration Pattern, arrival patterns
  Create a TR closure model
  Backlog = Arrivals minus closures
TR Closure model
  Simplest would be some number per day
  May need more complex based upon how much effort is going in to fixing TRs
  For example:
    Assume, on average, a programmer can close 1 TRs per day (lots of tools) pre-release when they work fulltime on bug fixing (use historical data)
    If we estimate # of programmers per day working fulltime on bug fixing, then can project closure rate

## Slide 54: Backlog Example
So…assume in our example we have 6 programmers and we estimate the % of programmers debugging each week.
  Not a constant number since more will be debugging at the end

## Slide 55: Backlog Model Example
Many adjustments possible to spreadsheet model. Possibilities:
More difficult bugs at the end – so less productivity
Programmers do not work 100% on new bugs at end
Creeping features?
Others?
Implication of chart:
When can ship with no backlog? [Can not really go negative]
Programmers are fixing bugs as per plan – no new features, etc.
Notes: Row 1 and Row 2 are from slide 41....Row 3 is an estimate...e.g., input to the model...and then we are assuming (slide 45) that you can fix 1 TR per day...
so, to figure out Row 4...you need calculate the number of TR fixes that are possible for that week.
So for week 7, you've got 6 programmers working 10% of their time fixing bugs...so that is 5days per week*6programmers*10%*1 bug per day = 3 TRs fixed that week. OK? see how that worked. and the next week, since we have the same amount of effort, we still have the potential for 3 bugs to be fixed per week.
row 5 is the TR backlog. for week 7, we had 3 TRs arrive, and 3 were fixed, so the backlog stayed at 0. For week 8, we had 10 new ones come in, 3 were fixed, and so backlog became 7. FOr week 9, 12 new, 3 fixed, so 9 more go to backlog for a total of 16....and so on....

## Slide 56: Commentary
Easy model to implement and understand
  Factors: Code Integration Plan, TR arrival rates (based upon Code), bug fixing productivity, % of effort fixing bugs
Easy to tweak
  Special weeks (Holidays)
  Plan changes
  Could add in break/fix as well if you wanted
Look at sensitivities easily  example, bug fixing productivity

## Slide 57: Backlog Model: Sensitivity to Bug Fixing Productivity
OK to ship dates from a backlog perspective: 1TR -~wk 21; .75 TRs ~ wk 23; 1.5 TRs ~ wk 18

## Slide 58: Sidebar Discussion
What does this tell you re: delivery date vs. TR fix productivity?
If you were the manager, what might you do?
Notes: Figure out how to have higher fix productivity – e.g., test beds, streamlined process, tools….

## Slide 59
Using Reliability Growth Models in Quality Management
  understanding where you are in the quality process
  These are variations of exponential in shape (rather than rayleigh)
  Concept is that quality should be continuing to improve…so fewer and fewer faults/failures are being found or experienced.

## Slide 60: Reliability Growth Models
Intended for Reliability Assessment
Useful for Quality Mgmt prior to ship
Compare to curves of previous projects
Use at the beginning of system test (or operational profile testing really)
  (Post code integration)

## Slide 61: How does this fit with the Rayleigh curves?
Rayleigh is for entire TR arrival
These are for ST -> Ship
Let’s look at Raleigh curve again
ST interval – exp shape
Again, this is dependent upon your testing methodology

## Slide 62: What does this mean?
What do you do now?

## Slide 63: Depends on Testing Effectiveness
Use the same type of effort/outcome matrix
  If you have reason to believe that the testing is much more effective, then …. Good
  If you don’t, then
    It means that your TR arrival rate in ST is well above previous project
    Need to implement Quality Improvement Program immediately
    Need to issue project advisory re: schedule

## Slide 64
  Recommendations for In-Process Metrics for Small Projects

## Slide 65: Recommendations
Front-end: Inspection/Review Evaluation
Middle: Code Integration Patterns
  Develop Heuristics over time
Back-end: Testing Defect Arrivals, Backlogs

## Slide 66
Testing Progress Metrics
    What do you think should be tracked?
    What do you think the curves look like?

## Slide 67: Test Progress Metrics
Planned vs. Attempted vs. Passed
Typically S-shaped Curves
Use historical data for planning
  If you don’t have any, create a plan anyway. It will be useful for the next time.
May want to weight test cases
  Most important vs. least (scale of 1 -> 10)
  [To start, have everything weighted the same]
+/- 15% should trigger alarms

## Slide 68: Example
What does this say?
What should you do?

## Slide 69: Example Response
This testing right now is in trouble
  Need to find what is holding up the successes
  Hopefully, one or two “blocking” fixes will unlock the successes.
Looks like testers are trying to test as much as possible – is this really effective if the issue is blocking TRs?
Possible actions
  Prioritize fixes immediately
  Divert more programmers to TRs if still doing features (or next phase features)
  Analyze TRs for patterns….is there some troublesome code? Do we need to inspect/have a QIP (Quality Improvement Plan) on something?

## Slide 70: Example cont
Find out 3 major blocking TRs
Will take 1 week to fix
Management Alternatives:
  See if testing can refocus on other areas
  Recognize testing is going to be stressed after turnover…if possible, give some time off now to help facilitate OT after turnover
  Alert higher mgmt to potential schedule/quality issues

## Slide 71: Stress Testing Metrics
Stress Testing is a different type of testing
  Typically looking at performance and capacity issues
  Trying to break the system by running huge volumes of transactions
    Looking for “heisenbugs”
Stress Testing Metrics need to look at
  CPU utilization by unit of test time (and any other areas of concern), Hangs & Crashes
  Create metrics such as weekly CPU hours per hang/crash index
Could be part of reliability testing process

## Slide 72
  Recommendations for In-Process Metrics for Small Projects

## Slide 73: Recommendations
Front-end: Inspection/Review Evaluation
Middle: Code Integration Patterns
  Develop Heuristics over time
Back-end: Testing Defect Arrivals, Backlogs

## Slide 74: Summary: In-process Metrics
In-process quality and schedule management
Need SMART milestones
Use Observable Events, not estimates
Can create simple models based upon these observable events
Reliability tools and techniques are applicable
  Don’t need to be quite as precise and stringent
  For management info rather than predicting reliability

## Slide 75: Benchmarking
What is Benchmarking?

## Slide 76: Benchmarking Definition
A point of reference from which measurements can be made

## Slide 77: Why Benchmark?
Must start with a knowledge of where you are
Allows comparisons both internally and externally to drive improvement activities
Allows learning from others experiences
Thru continuous benchmarking, measure success of improvement activities

## Slide 78: Internal Benchmarking
First step
Allows identification of internal best practices
Allows identification of improvement opportunities

## Slide 79: External Benchmarking
Looks at how others performs
Issues with sharing of data between companies
Can be used to look for competitive advantages and to drive strategy and technology advances
Examples:
  Cost of development staff
  Time to build an interface

## Slide 80: Some External Benchmarks
Quantitative targets for DOD projects - You guess
Ref: NetFocus, 1995

## Slide 81: Some External Benchmarks
Quantitative targets for DOD projects
Ref: NetFocus, 1995

## Slide 82: Homework
Why would you use the effort/outcome matrices?
Given the following code integration schedule, an expected defect density of 5 TRs per every new/changed KLOC, and assuming TRs are surfaced at the rate of: 30% in 1st week. after turnover, 35% in 2nd week, 20% in 3rd, 10% in 4th, 5% in 5th
  What is the projected TR arrival graph?
  Given that you have 15 programmers on the project, and each can fix 1 TR per day (when that is all that they are doing), graph the backlog.
  If your ship criteria is < 5 TRs in backlog, what week can you ship?

## Slide 83: Homework cont.
Why do you care about CPU utilization in stress testing? Why do you care about CPU hours per week in testing?

## Slide 84: Homework
Why would you use the effort/outcome matrices?
  To understand the quality of the process execution in order to better understand the in-process data such as defects found
Given the following code integration schedule, an expected defect density of 5 TRs per every new/changed KLOC, and assuming TRs are surfaced at the rate of: 30% in 1st week after turnover, 35% in 2nd week, 20% in 3rd, 10% in 4th, 5% in 5th
  What is the projected TR arrival graph?
  Given that you have 15 programmers on the project, and each can fix 2 TR per day (when that is all that they are doing), graph the backlog.
  If your ship criteria is < 5 TRs in backlog, what week can you ship?
  TR arrival graph will be- 5* (.3*KLOC previous week+.35*KLOC 2 weeks ago+.2*KLOC 3 weeks ago+.1*KLOC 4 weeks ago+.05* KLOC 5 weeks ago)
  Use numbers given for programmers working on fixes. Multiply that by 15*2*5 to get number of potential fixes per week. Subtract # fixed from backlog and new arrivals to get new backlog. Adjust so it doesn’t go below 0. See when ship date is

## Slide 85: Homework cont.
Why do you care about CPU utilization in stress testing? You want to be running your CPU over 60% during stress testing. Otherwise the test is invalid. Why do you care about CPU hours per week in testing? In order to make some sense out out of defect arrival data per week.

## Slide 86: Theater Tickets Project – 2 Parts
Part 1:
  What benchmarks do you think are relevant for the theater ticket project? Include both the name of the metric, the value that should be used for comparison, and the rationale.

## Slide 87: TT Project Part 2
Create a Trouble Report Arrival Plan based upon:
  10K Lines of Code
  Integration Plan:
  You expect TR arrival to be algorithmically: 10%, 80%, 10% per week after turnover
  You expect to find 10 defects per KLOC before you ship
Create a Backlog Plan
  Expectation is that each programmers can fix 2 TRs per staff week) if they work full time at it - 10 programmers on job
  Plan on 10% fixing per turnover date, 100% after turnover date
  When will the backlog be cleared out?
Create a 2nd Backlog Plan
  Plan on 10% fixing until week 6, when 50% start to fix troubles, then 100% after turnover
  When will the backlog be cleared out?