## Slide 1: Software Engineering 533: Software Metrics and Economics
Linda M. Laird
Lecture 7
Estimation Part 2
Stevens Institute of Technology

## Slide 2: Agenda
Custom Models
Tools
Algorithmic Models
  Overview
  Example
Uncertainties
When to Estimate
Recommendations

## Slide 3: Custom Models
Concept: If you understand the cost drivers of your system well, then you can come up with a custom model to use in estimation which may be easier and more effective to use than the other models.

## Slide 4: Custom Models
4 parts of Process (DeMarco)
  Decomposition of Costs
  Formulation of a Cost Theory
  Data Collection
  Statistical Correlation

## Slide 5: Example: Custom Models
Issue: For HFC Switch Assignment, need to estimate 40 new features for each release, with 4 releases per year
  Cost per estimate using existing methodology (bottom-up, from scratch) = 1 staff week; For all 160 features, 160 staff weeks per year – fully loaded cost > $450K!
Solution: Develop a custom estimation model
  Step 1: Decompose the costs

## Slide 6: Example: Step 1: Decompose the costs.

## Slide 7: Example: Step 2: Formulate a Cost Theory
Theory – cost is based upon 2 variables – number of data base schema changes and number of interface changes
Estimate typical impact (in weeks) in each sub-area for a database change and an interface change

## Slide 8: Ex: Step 2 cont: Formulate a Cost Theory

## Slide 9: Step 2 – Part 3
Possible Cost Functions:
  If
    NDB=number of database changes,
    NI=Number of Interface Changes
    CDB=Complexity of DB Changes
    CN=Complexity of Interface changes
  Then
    Formula 1:
      Cost = f(NDB, NI), which =15*NDB + 10*NI
    Formula 2:
      Cost=f(NDB, CDB, NI, CN)=15*CDB*NDB + 10*NI*CN
Note: this is just an example with some made up cost functions.

## Slide 10: Step 3: Gather Data

## Slide 11: Step 4: Correlation
Now what do we do?
  Graph it, Look at it, Try some analysis

## Slide 12: Step 4: Analysis Cont:

## Slide 13: Step 4 Cont.

## Slide 14: Example: Commentary
Either formula looks fine
  Within 25% (!!!) for algorithmic models is pretty good.
Might as well use #1 because it is simpler, and actually seems to work better

## Slide 15: Custom Model Review
Developed an underlying data model and cost estimation model for specific application
  Gathered data, looked at statistics, validated model.
    Need to continue to gather data for estimates vs. actual
  Cost per estimate decreased from 5 days to…..2 or 3 hours?
    Hypothetical Cost reduction > .9*$450k=$405k!
All relatively simple to do

## Slide 16: When should you use custom models?
When you have multiple projects that you think are relatively similar – such that you think a cost theory might work.
Go for simple correlations and factors first
And remember, the standard tools typically are not very precise…

## Slide 17: Estimation Tools
History
Key Features
Example
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 18: History of Estimation Tools
1970 – 1980
  FPs developed
  Initial Tools – SLIM and Price-S
1981 – COCOMO 1 Models, equations developed
1985 – 2000 Estimation Tool Market expands
2000 – COCOMO 2
2002 – > 50 Commercial Tools in USA
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 19: Tools
Cocomo, SPR, & Checkpoint are primary ones estimation tools….many items as input
  Software Taxonomy
    Nature (new, old, conversion, enhancement)
    Scope (small…eg, module or large, eg. System)
    Class (Internal vs. External, Civilian vs. Military)
    Type (system, application, embedded, info system)
  Project Goals
    Standard estimates vs. shortest schedule with extra staff vs. lowest effort w/reduced staff vs. highest quality w/normal staff vs. highest quality with shortest schedule vs. highest quality with least effort.
  Work Patterns, Staff Salaries, and Overhead Rates
    E.g., Staff availability, average work week, work hours per day, effective work hours per day, OT per week, work days per year, OT premium pay, average Salary, burden rate

## Slide 20: Model Input, continued.
Preliminary Size estimate
  Supplied by user
  Estimate based on scope, class, & type
  Based on FPs, analogy, LOC
Outputs:
  Start, Completion, Schedule, Staff, Effort, Costs
These tools are typically estimation and PLANNING tools…note that they require SIZE as an input

## Slide 21: Overview of Features of Current Tools
Sizing logic for specifications, source code, and test cases
Phase-level, activity-level, and task-level estimation
Support
  FPs and LOC
  OOT
  backfiring/conversion between LOC and FP
  software reusability of various artifactstraditional languages such as Cobol, Fortran, and for modern languages such as Java and Visual Basic
Quality and reliability estimation
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 22: Add’l features found in some tools
Risk and Value Analysis
Estimation Templates from historical data
Links to Project Mgmt Tools
Cost and time-to-complete estimates mixing historical data w/project data
Inflation calculations for long-term projects
Estimates keyed to the SEI Model
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 23: Estimation Features to come
Internationalization costs
Fees for trademarks and copyright searches
Acquisition costs for COTS
Deployment costs for ERP apps
Litigation costs if project is late or over budget
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 24: Generic Features in Estimation Tools
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 25: 1) Sizing specs, source code, and test cases
Usually with
  FP as the input
  some take LOC
  some take Use Cases
Output
  Specification, source code, test case, user documentation volumes
Estimation of feature creep
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 26: 2) Selecting Project Activities/Process
Range of Activities possible
  Web Projects – 8 activities
    Rqmts, Prototyping, Coding, ReUse Acq., Testing (2), Documentation, Project Mgmt
  MIS Projects – 18 activities
    Includes other activities such as project planning, initial design, detailed design, config mgmt, architecture,
  Systems Projects – 23
    Include other activities w\such as design reviews, code inspection, field testing
  Military – 25 activities
    Independent Testing (2)
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 27: 3) Estimating staffing Levels
Including different levels and different specialties – up to operational groups
  Different cost levels
  On project for different lengths of time
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 28: 4) Estimating Software Work Effort
Includes vacation days, training, lengths of work weeks, typical number of hours per day
Usually need measurement of existing environment for accurate data
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 29: 5) Estimating Software Costs
Costs per specialist vary by location and by company
  3 to 1 inside of the US
  10 to 1 globally
Need to include fully burdened costs (e.g., overheads)
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 30: 6) Estimating Software Schedules
May be done by estimation tool alone, or in concert with a project mgmt tool
Typically complex due to interaction and dependencies between activities, overlapping & concurrent activities, overtime, actual vacations etc.
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 31: 7) Estimate Defect Potentials
Defect removal may take more time and cost than any other project activity
Uses an estimated defect potential rate
  [More details on how this is estimated in later lectures]
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 32: 8) Estimating Defect Removal Efficiency
Input the kinds of defect removal activities, and estimated effectiveness
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 33: 9) New Technology Impacts
Many tools have built-in assumptions regarding process improvements
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 34: 10) Estimating Maintenance Costs over Time
Common metrics used:
  Defects repaired per time unit
  Assignment scope: 300 to 5000 function points – average ~1000
Jones: “Software Cost Estimation
in 2002”, Crosstalk, 6/02

## Slide 35: Summary re: Tools Features
Can be detailed re: amount of input required
Reasonable input being requested
  They are significant cost drivers
Models are relatively sophisticated and can help a lot, especially when tied with project management tools
Tuning is required.
  [NOTE: some more recent studies suggest that when using standard cost factors (e.g., COCOMO-like factors, Function Points), organization specific models did not yield better results than generic, multi-organization models- easier to use tools.]

## Slide 36: Tools:
Many commercial tools available, many as freeware.
Most popular are Cocomo, SPR tools, and Knowledge plan; most are based on Cocomo model(s) and variations
See reading for tool review and references.

## Slide 37
Algorithmic Models

## Slide 38: Algorithmic Models
Typical estimation model is of the form
  E = A + B * (ev)**C
  Where A, B, C are empirically derived constants, E is effort in staff-months, and ev is the estimation variable (either LOC or FP)
LOC or FP
Effort

## Slide 39: KLOC Algorithms
E = 5.2 x (KLOC)**.91 Walston-Felix Model
E= 5.5 + .73 x (KLOC)**1.16 Bailey-Basili Model
E = 3.2 x (KLOC)**1.05 Boehm Simple Model
E = 5.288 x (KLOC)**1.047 Doty model for KLOC >9
Clearly……all give different results, and must be used/ calibrated with care.

## Slide 40: Comparison of Algorithmic KLOC Models

## Slide 41: FP-oriented Estimation Models
E=-13.39 +.0545 *FP Albrecht & Gaffney
E=60.62 + 7.728 * (10 -8) *(FP3) Kemerer Model
E = (FP1.4)/150 Jones rules of thumb

## Slide 42: Effort Prediction Algorithms – FP

## Slide 43
What do you think about the different results that the models give? Are you surprised?

## Slide 44: Comment on “Simple Algorithms”
Some of these models were derived from very specific environments on small data samples
The most important number is the power to which FPs/LOC are raised.
Calibrate what you are doing….and if it works, great…if not, keep adjusting or use different techniques.

## Slide 45: Cocomo: Constructive Cost Model
Barry Boehm’s Model – Extremely Famous – from 1981 – most widely used and discussed
Continued to evolve to Cocomo II in 96, and extended in 2000….more flexible, more complex, handles more methodologies

## Slide 46: Cocomo 1
Basic Cocomo: E=b*KLOCc; (E == Effort)
3 Classes of Projects:
  Organic – small experienced team, known environment. Projects tend to be small. Examples?
  Semi-Detached – mixture: Examples?
  Embedded – embedded in an inflexible environment … such as a weapon control system: Examples?
Effort Coefficients:
  Organic: b=2.4, c=1.05
  Semi-detached: b=3.0, c=1.12
  Embedded: b=3.6, c=1.20
For Duration, D=2.5*Ef, where
  Organic: f=.38
  Embedded: f=.35
  Semi-detached: f=.32
Effort is the primary Equation – Duration is very much a secondary one.

## Slide 47: Cocomo 1

## Slide 48: Intermediate Cocomo
Refinement – most commonly used model
15 attributes for a product, and a six point scale
Attributes:
  Product: Required reliability, amount of data, complexity
  Computer attributes: time & memory constraints, volatility, turnaround time
  Personnel: Capability, Experience
  Project: Methodology, tools, and Schedule
Use the weighted attributes to adjust the basic equations.
Boehm states that intermediate Cocomo produces sound results “within 20%, 68% of the time.” … e.g., 1SD

## Slide 49: Cocomo II – Key differences
Estimation based on 3 major stages of a development project – with different techniques for each.
  Stage 1: No KLOC estimates available, so uses object points …which are high-level effort generators such as server data tables, number of client tables, % of screens and reports reused
  Stage 2: Go decision on development, but must explore architecture, etc. Still not enough info for KLOC, so uses FPs.
  Stage 3: Can estimate KLOC, and takes into account reuse, breakage, etc. to produce schedules.

## Slide 50: COCOMO models
Based on data from 1000+ projects
Frequently in the aerospace, DOD domain

## Slide 51: Cocomo Extensions
Add’l variations and extensions of COCOMO under development – such as for Reuse and COTS

## Slide 52: What do you think of these results?
“Within 20%, 68% of the time”

## Slide 53: Use Case Point Studies – Bente Anda – Simula Research Labs
Company | Pro- ject | Use Case Estimate | Expert Estimate | Actual Effort | Deviation use case est. | Deviation exp. est.
Mogul | A | 2550 | 2730 | 3670 | -31% | -26%
Mogul | B | 2730 | 2340 | 2860 | -5% | -18%
Mogul | C | 2080 | 2100 | 2740 | -24% | -23%
CGE&Y | A | 10831 | 7000 | 10043 | +8% | -30%
CGE&Y | B | 14965 | 12600 | 12000 | +25% | +5%
IBM | A | 4086 | 2772* | 3360 | +22% | -18%
Students project | A | 666 |  | 742 | -10% | 
Students project | B | 487 |  | 396 | +23% | 
Students project | C | 488 |  | 673 | -25% | 
Notes: <number>
<footer>
<header>
<date/time>

## Slide 54
Why aren’t the results better?
Is software estimation an engineering process? Or art?.... Or impossible?

## Slide 55
“…if software estimation is believed to be a codifiable engineering process analogous to house building then litigation is a reasonable and expected consequence of inaccurate estimations.”
Terry Bollinger, "The Interplay of Art and Science in Software," Computer, vol. 30, no. 10, pp. 128,125-127, Oct., 1997.

## Slide 56: 2 Camps in SE Community
The “process” camp:
  Quality software can be developed on time if a particular software process or programming technology is used
The “problem solving” camp:
  Programming is fundamentally a process of solving problems and as such intrinsically resists codification.

## Slide 57: More from the problem solving camp
“The creation of genuinely new software has far more in common with developing a new theory of physics than it does with producing cars or watches on an assembly line.” --- T. Bollinger

## Slide 58: Software Development: Process Execution or Problem Solving?
Or

## Slide 59
What do you think? Or the execution of a process? Is programming problem solving?
Does it vary, based upon the circumstance?

## Slide 60: Limitations of Estimation – Why?
The question is whether you are dealing with anything new or unknown
…You almost always are…
The questions become how to bound and manage the uncertainties…

## Slide 61
Models and Methodologies are not a replacement for Common Sense and Engineering Judgment
Need to use all of them

## Slide 62: Barry Boehm’s Cone of Uncertainty - 1981
Relative Cost Range
x
1.25x
1.5x
2x
4x
0.8x
0.5x
0.25x
0.67x
Phases and Milestones
Feasibility
Concept of Operation
Plans and Requirements
Requirements Specifications
Product Design
Product Design Specifications
Detailed Design
Detailed Design Specifications
Development and Test
Accepted Software

## Slide 63: Today’s View---Approximately
Relative
Cost
Range
x
1.5x
2x
075x
0.5x
Phases and Milestones
Feasibility
Concept of Operation
Plans and Requirements
Requirements Specifications
Product Design
Product Design Specifications
Detailed Design
Detailed Design Specifications
Development and Test
Accepted Software

## Slide 64: Remember what an estimate is…
It tends to be the most likely view….and it is equally likely to be over as well as under……remember statistics…

## Slide 65: We need to
Accept and consciously deal with Estimation Uncertainties
  Understand, accept, and manage the inherent uncertainties in estimation
  Change our terminology in estimation to include the uncertainties

## Slide 66: Uncertainty does vary over time
Relative
Cost
Range
x
1.25x
1.5x
2x
4x
0.8x
0.5x
0.25
0.67x
Phases and Milestones
Feasibility
Concept of Operation
Plans and Requirements
Requirements Specifications
Product Design
Product Design Specifications
Detailed Design
Detailed Design Specifications
Development and Test
Accepted Software
Boehm’s 1981 Cone of Uncertainty

## Slide 67: What are estimation uncertainties?
Statistical Variance
  Always will exist
  Only question is size
  Repeatable Processes -> Reduction in this variance
Known Risks
  Use Risk Management Plan
  Add contingencies
Unknown Risks
  Use experts to minimize them
  Use Management Contingency
    Based on expected invention required
    PMI recommends 10% if nothing else known

## Slide 68: Change how we speak & think about estimations
Which is better?
  12 staff months
  12 staff months – 50% of the time it will be less, 50% of the time, it will be greater (except for parkinson’s law)
  95% of the time between 10 and 14 staff months
  95% of the time <= 14 staff months
Notes: Sharing risks in last 3

## Slide 69: Estimation Terminology
Estimations, especially early in the process, are just predictions. They have a probability of being accurate…with a range of likely variance. Need to reflect probability and expected variance (e.g., uncertainties) in estimations
X% View
  Means there is a X% chance of not exceeding the estimate
Probability Intervals -- Ranges -- representing expected variance
  Between Y and Z staff months or even
  90% view is that it will be between Y and Z staff months

## Slide 70: Determining Probabilities
50% view is typically what is estimated
  Experts (and some tools) will give you the ranges as part of the estimation process
Unfortunately, studies have shown that the experts are typically over-confident.
Estimation ranges from organizational baseline engineering rules or default engineering rules are typically more accurate

## Slide 71: Example: Organizational Eng. Rules
Assume your estimate is 10 staff years, and on previous similar projects,
  10% came in under budget by 10%,
  30% came in on budget,
  40% came in over budget by 50% and
  20 % came in over budget by > 50%.
Then your %estimates are:
  10% estimate - 9 staff years,
  40% estimate - 10 staff years
  80% estimate – 15 staff years
Notes: The 10% estimate --> you want to use the data that 10% came in
under budget by 10% (just happened to be the same number)
--> which in this case happened to be 1 staff year.
So it is reasonable to think that 10% of the time you will be under estimated on this project by 10% or 1 staff year.
So the 10% view is 9 staff years.
Now, using the 30% came in on budget -- that means that the 40% view (30+10=40) is coming in on or less than budget...and that is at 10 SY.
Now using the 40% coming over budget by 50% means that 80% (10+30+40) came in <= 50% over which is 15 staff years.
The thing to remember is the X% view means that X% of the time you will not exceed that number.
I believe this is what you don't quite get...
please correct me if I'm wrong
Example: From project data
Assume your 50% estimate is 10 staff years, and on previous similar projects,
30% came in on budget,
10% came in under budget by 10%,
40% came in over budget by 50% and
20 % came in over budget by > 50%.
Then your %estimates are:
10% estimate - 9 staff years,
40% estimate - 10 staff years
80% estimate – 15 staff years
Note that you really don’t have a 50% estimate any more.
Lets look at the 10% estimate. This means that 10% of the time, the project would
be done by this date. OK, so in the past, 10% of the projects came in 10% under.
10% of 10 is 1, so our p10 number 9 staff years.
Now 30% came in on budget. That means 40% (30+10) came in on or BELOW budget.
Therefore, our 40% number is 10 staff years. That is, we expect that 40% of the time,
the project will be done <=10 staff years.
Now another 40% came in 50% overbudget, which would be 15 staff years. So, 80%
(40+30+10) of the time, we expect the project to be done in <=15 staff years.
etc.
Ok NOw? Sorry if it wasn't clear.

## Slide 72: Engineering Rules for Estimation Uncertainty - Default
Defaults by Phase:
  Feasibility + 100%, - 50%
  Rqmts + 50%, - 25%
  Design + 20%, - 10%
  Coding +10%, - 5%
  Testing +5%, - 2.5%
Example:
  Your current 50% estimate is 30 staff months, and you are in the design phase
  You’d say that the expected range is between 36 and 27 staff months

## Slide 73: Estimation Uncertainties - Summary
Change your terminology to X% views and ranges
Use methods other than gut feelings for determining the ranges
  Either engineering rules or organizational history

## Slide 74: Combining Estimates
Always recommend 3 or more estimation methodologies -- “Triangulate” on your answer
  Many of the methods are simple to use
Want to use complementary ones
  Do not select the same methods with the same biases.

## Slide 75: Selecting methods
Methods that would be considered complementary would be:
  Top-down with bottom up
  Expert opinion with Analogy
  Expert opinion with Proxy Points
  Expert opinions by experts with different project experiences and responsibilities
  Proxy points and Analogy
Methods that would be considered to have the same biases would be:
  Algorithmic Models based on the same underlying algorithms (such as all of the COCOMO derivatives)
  Experts who have had the similar responsibilities on similar projects[i]
[i] Jorgensen, Magne, Practical Guidelines for Better Software Estimation, 2005

## Slide 76: Use and Accuracy of Estimations
Remember: The need for accuracy of an estimate is related to its purpose at that point in time.
Feasibility stage:
  need only be accurate enough to support a decision to prepare a more detailed definition of the project.
Requirements specification
  Critical project decision point
    You are potentially committing significant resources based on the business case, which is based upon the cost estimate.
Detailed Design Complete:
  hopefully most of the unknowns have become known, and a reasonably accurate estimate and plan can be created.

## Slide 77: Combining Estimates
Always recommend 3 or more estimation methodologies
Want to use complementary ones
  Do not select the same methods with the same biases.

## Slide 78: Combining Estimates
Arithmetic Combinations
  Mean with SD
  Weighted Mean
    Normal Distribution
    Expected Validity

## Slide 79: When to Estimate
Due to inherent uncertainties throughout a project, need to re-estimate as you learn more.
Whenever you have major unplanned events, you’ll need to understand how they impact the schedule and the effort.
Even without those events, you should estimate the job at least three times:
  Feasibility Phase – Macro Estimation
  Requirements Phase – Detailed Estimation
  Design Phase– Refined Estimation
Estimate “early and often”
  allows you to take appropriate action to adjust the program and project plan when you find the work is not totally aligned with the budget

## Slide 80: What do people actually do?
Expert Estimation is most frequently used
Ref: “A Review of Surveys on Software Effort Estimation” : Molokken and Jorgensen, Simula Research Laboratory, 2003

## Slide 81: One final issue: Target vs. Estimation
This is a big question
  Are you being told or asked?
But….even if you are told the answer, all of the same tools and techniques apply
Vs.
?

## Slide 82: When you are given the answer
The answer is the effort budget
Then you need to:
  Size the job as it is currently defined
  Understand quantitatively the difference between the budget and what you estimate
  Work to bring the budget and your estimate into alignment

## Slide 83: Aligning the budget and the estimate
Reducing your estimate by
  Decreasing the cost drivers and risk factors…for example, by
    Simplifying design, reducing complexity, reusing components, omitting optional functionality etc. etc. etc.
  Increasing productivity by
    Using more productive language, using higher skilled people, better technology, etc
Attempt to increase budget by demonstrating quantitatively the reasons and sources of the estimate

## Slide 84
My Three Final Recommendations

## Slide 85: The Golden Rule of Estimation
Require all estimates to be justified
  Gut feeling is not an adequate justification

## Slide 86
Do Not Use Tools or Methods Blindly
Try estimating previous projects to validate/tune methods

## Slide 87: Education and Training Work
Train your estimators
Knowing how to do something doesn’t mean you know how long it will take
Need to train estimators – accuracy correlated with training and ability to see results (and responsibility), rather than development experience

## Slide 88: Homework - All Required
Read: REQUIRED
  20 Deadly Sins article
  Software Tools articles
  Effort Estimation article
  Anything other articles posted on website

## Slide 89: Automated Estimation Project
Select 2 automated tools
  Use it to estimate theater tickets
  Compare it with the estimates you’ve previously made
  In your project, include
    Algorithms and approach it takes to estimation
    What do you think of the tools
You can download demo version of the tools usually.
  Some tools – Duvessa, Estimate Professional, Slim, Costar, CostExpert – you can find them if you look.
  You may have trouble with size of project….figure out something
  http://www.thedacs.com/databases/url/key.hts?keycode=4:152&islowerlevel=1

## Slide 90: Selection of Tools –
ACEIT (Automated Cost Estimating Integrated Tools) ACEIT helps analysts store, retrieve, and analyze data; build cost models; analyze risk; time phase budgets; and document cost estimates. It is a generic, flexible, Windows-based system you can use to estimate virtually any task on any type program. The result of government-sponsored efforts, the ACEIT suite of applications is available to U.S. Government organizations with no charge for use.
Bournemouth University -- ANGEL Project Estimation by analogy, is the focus of a research project being undertaken by the Empirical Software Engineering Research Group (ESERG) at Bournemouth University. A brief bibliography and the downloadable ANGEL tool are provided.

## Slide 91: P2
COCOMO Project Homepage The COCOMO II model is an update of COCOMO 1981 to address software development practices in the 1990s and 2000s. It is being developed by USC-CSE, UC Irvine, and 29 affiliate organizations. A public version of COCOMO II is available, including a Java implementation.
COOLSoft COOLSoft utilizes a hybrid approach of intermediate and detailed versions of the Constructive Cost Model (COCOMO). This allows for the reuse of existing code, development of new code, the purchase and integration of third party code, and hardware integration. The output is then displayed as man-months of programming effort, calendar schedule, support costs and hardware costs.
CoCoPro Based upon Barry Boehm's constructive cost modeling methods, CoCoPro estimates resources needed to complete a software development project. The program uses exponential functions and attributes to calculate development costs.

## Slide 92: P3
Construx Software Builders Construx Software Builders provide Construx Estimation Software, a free estimation tool that includes both COCOMO II and SLIM functionality.
Cost Estimating Tools Index This index contains abstracts of tools and models that are currently used in the Department of Defense and have the potential for wider application.
Cost Estimation Resources This site provides access to a collection of cost estimation resources hosted by Contrux.
Cost Spreading Calculator This is a simple online cost spreading calculator that can be used to spread the estimated cost of a program up to 8 years. The calculator uses a beta curve to determine the amount of money to be spent in each year based on the fraction of the total time that has elapsed. The user enters the total cost to be spread, the beginning and ending years.

## Slide 93: P4
Cost Xpert This software cost estimation tool from Cost Xpert Group is calibrated to reflect the latest industry standards. It generates cost and schedule estimates and automatically generates a work breakdown structure (WBS) to use as a starting point for a project plan. It is also tailorable to fit your organization’s processes and COTS implementations.
Costar Software Estimation Tool Costar is a software cost estimation tool based on COCOMO II. A software project manager can use Costar to produce estimates of a project's duration, staffing levels, effort, and cost. Costar is an interactive tool that permits managers to make trade-offs and experiment with what-if analyses to arrive at the optimal project plan.
East Tennessee State University -- COSMOS This software project estimation and analysis tool gives project managers insight into the size, effort, and schedule of their software development project. This tool is unique in that it combines the well-known Function Point and COCOMO models as well as a Rayleigh model of staff buildup proposed by Lawrence Putnam. These three models can be used independently or work together. With COSMOS, users can gain an understanding of changes in project requirements and resources that impact the project's size, effort, and schedule. Furthermore, COSMOS is ideal for helping educators provide students with insight into how the function point and COCOMO models work.

## Slide 94: P5
Galorath Incorporated (also known as GA SEER™ Technologies) Galorath provides a comprehensive set of decision-support and production optimization tools. Consulting and support services are available for these tools. The tools help manage product design and manufacturing operations, driving out costs and building in quality. The tools derive cost, schedule, labor and materials estimates by assessing the interaction and impact of product, organizational and even operational variables.
Online Cost Models This page maintained by NASA is a link to on-line Cost Estimation Models and calculators.
PRICE Systems LLC PRICE S can be used to estimate selected portions of a software project, or to comprehensively estimate the entire project, including all development, modification, and life-cycle costs. It also provides sizing applications that make it easier to determine the size of the project to be estimated.
Quantitative Software Management (QSM) Lawrence Putnam is the president of QSM. QSM offers their clients Software Lifecycle Management (SLIM) processes and tools for software cost estimating, reliability modeling, schedule estimating, planning, tracking, and benchmarking.

## Slide 95: P6
REVIC Software Estimation Model SEPO has made available version 9.2 of the Revised Intermediate COCOMO Model (REVIC), which is sponsored by the Air Force Cost Analysis Agency.
RiskTrak Home page for Risk Services & Technology and RiskTrak, their software management tool. RiskTrak is risk management groupware that allows you to view, analyze, communicate, report and manage risk (cost, schedule & technical) throughout the duration of your projects and programs. RiskTrak is designed to help businesses meet new standards on Risk Management such as: Clinger-Cohen Act (ITMRA), Department of Defense Directive 5000.2-R, CAIV and OMB Circular A-11. RiskTrak supports Best Commercial Practices and is designed to be integrated with any Earned Value Management System (EVMS).
SchemeQuest SchemeQuest offers an inexpensive Excel add-in, SCEplus, which provides a complete COCOMO II cost modeling capability. A free fully functional 30-day demo version is available for download.
Softstar Systems Developers of Costar, an automated implementation of COCOMO II