9. Introduction

This section discusses special considerations for development of Architecture and User Requirements documents, identifies deliverables, and presents detailed schedule and resource information.

9.1 Special Considerations

The items discussed below have been identified as issues that must be addressed during development. The estimation and scheduling process has included their impact.

We had an Architecture Discovery session, and shall have an Architecture Review before baselining the Architecture.

There is limited additional work on requirements beyond the RFP, given the simple nature of the system. It is necessary, however, to define the interfaces among the various computers. It is stated that the workstation-IBM/UNIX interfaces are well documented and that the documentation is correct. We anticipate that this needed to be confirmed at a minimum.

9.2 Deliverables

The following product definition deliverables are required:

| Deliverable | Supplier | Customer | Accept Criteria | Due Date | CWV | Actual Date |
| --- | --- | --- | --- | --- | --- | --- |
| Architecture |  |  |  |  |  |  |
| Preliminary Architecture | F. Lloyd Wright | Project Manager | Arch Review |  |  |  |
| Final Architecture | F. Lloyd Wright | Project Manager | Arch Review |  |  |  |
| Requirement |  |  |  |  |  |  |
| CCPS Transaction Specification | R. Q. T. Writer |  |  |  |  |  |
| IBM Interface Specification | R. Q. T. Writer |  |  |  |  |  |
| UNIX Interface Specification | R. Q. T. Writer |  |  |  |  |  |
| If you’ve done a detailed task list using “cards-on-the-wall,” you’ve got most of this, enough for the “preliminary plan.” There’s no need to fill this table for the course |  |  |  |  |  |  |

9.3 Development Estimates

9.3.1 Estimation Approach

[How were the estimates made? Examples of size measures are function points, lines of code, pages, gates, etc. Examples of processes are Delphi method, expert opinion, automated systems, etc.]

9.3.2 Scope of Estimates

[What’s in the estimates, and what’s not? What tasks are covered, and what are not? For example, a typical preliminary software estimate may include design, code, and unit test, all design documentation, and be loaded with inspection and review effort. More refined estimates will split out the piece parts.]

9.3.3 Estimation Results

The table below shows the estimation results for the definition deliverables of CCPS. User documentation, project documents, hardware, and software development are treated separately. The data below corresponds to the intervals shown in task lists and Gantt charts.

| Deliverable | Size | Duration | Effort |
| --- | --- | --- | --- |
| Preliminary Architecture |  |  |  |
| DO A SAMPLE ONLY FOR COURSE |  |  |  |

9.4 Detailed Scheduling

The table below shows the final results of scheduling and staffing for the definition portion of CCPS. The “task” level appears on the project task list.

| Deliverable Task Sub-Task | Supplier/Resp | Duration | Due Date | CWV | Actual Date |
| --- | --- | --- | --- | --- | --- |
| Product Architecture |  |  |  |  |  |
| Develop Prelim |  |  |  |  |  |
| Arch Review |  |  |  |  |  |
| Draft |  |  |  |  |  |
| Review |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Develop Final |  |  |  |  |  |
| Arch Review |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Inspect 1 |  |  |  |  |  |
| Baseline 2 |  |  |  |  |  |
| CCPS Transact Spec |  |  |  |  |  |
| Task A |  |  |  |  |  |
| Sub-task 1 |  |  |  |  |  |
| Sub-task 2 |  |  |  |  |  |
| Sub-task 3 |  |  |  |  |  |
|  |  |  |  |  |  |
| Task B |  |  |  |  |  |
| If you’ve done a detailed task list using “cards-on-the-wall,” you’ve got all this, at least at the “preliminary plan level.” There’s no need to fill this table. Later on, however, such things as inspections and reviews will show up in this. |  |  |  |  |  |

Explanatory Notes

We have divided project deliverables into four classes, with corresponding special project plan sections, as shown below:

- User Documents

- Product Definition

- Hardware

- Software

There are more possible deliverables than these, e.g., the project plan itself. Cover the development of significant deliverables somewhere that makes sense, at a minimum, in the task list. If necessary, create a new plan section called, e.g., Project Deliverables.

Any design document requiring much effort (almost all of them) should be identified as a specific deliverable, have an associated task, and be scheduled and tracked, at least in the final plan.

Size of the deliverable in a reasonable unit, e.g., lines of code or feature points for software, gates or devices for hardware, lines or pages for documents. Always estimate the size and effort separately. The size is an inherent attribute of the product, given that a certain technology is chosen. The effort depends on how the job is done, for example, on the skill of the specific person doing the work.

The “task/sub-task” approach allows you to get to sufficient detail for accurate scheduling, but can keep the overall number of tracking items manageable at the project level. Tasks go on the project task list, but sub-tasks don’t.