7. Introduction

This section identifies User documents required for the CCPS Project, and provides detailed information about them, e.g., ownership, development schedules, etc. Non-User documents are covered in other Project Plan sections, but the overall documentation scheme is discussed below.

7.1 Overall Documentation Scheme

Project documentation work has been divided into the classes identified below.

7.1.1 User Documents

The User documentation development is minimal, comprising a Users Manual and Error Manual. In addition, the system will have a variety of “Help” screens, and these are being considered as documents as far as design (information content, location, etc.) is concerned. They will have to be actually implemented in software. The implementation of the Help screens is included in the software estimates, and this section refers only to their design.

7.1.2 Design Documents

These are the documents essential to building the product, such as requirements, architecture, and design. All are covered elsewhere in the plan, as they are not (primarily) user documents.

- Product Definition Documents: the system-level documents are the following:

- System Requirements Specification (given in the RFP)

- Architecture Specification (Reference 2, summary in Section 3)

- The first two of the above exist as of the writing of this document, and the third is in preliminary form.

- Software Documents:

- Detailed requirements

- Detailed design

- Test plans

- Following the MSDS methodology, the first two documents above are combined into one, and are jointly produced by a systems engineer and developer.

- Hardware Documents: since we have chosen to purchase the circuit pack from an external vendor, the only document required here is a detailed specification, which will then become an attachment to the board contract.

7.1.3 Test Documents

Test documents include test plans, scenarios, scripts from integration test onward. Unit test documentation is included as design documentation.

7.1.4 Project Documents

The primary project document is the Project Plan, of which this is the preliminary version. Both preliminary and final versions are covered in the task list.

7.1.5 Production Documents

This product will be manufactured externally, so that no documents are needed.

7.1.6 Installation Documents

An Installation Manual may or may not be required, depending on the extent of Customer involvement.

7.1.7 Other Documents

- ATCO contract

- BoardTech contract

Both contracts remain to be done, assuming that we win the job. Some negotiations with the board vendor have occurred. Both contracts are included as project tasks.

7.2 Special Considerations

Document preparation will be done by external professional writers, who will use the project staff as resources.

Documents will conform to the standards identified subsequently.

7.3 Required User Documents

| Deliverable | Supplier | Customer | Accept Criteria | Due Date | CWV | Actual Date |
| --- | --- | --- | --- | --- | --- | --- |
| User’s Manual | External writer | HPE person (for ATCO) | Inspection |  |  |  |
| Error Manual | External writer | HPE person (for ATCO) | Inspection |  |  |  |
| “Help” screens | HPE person | SW Devel | Inspection |  |  |  |

7.4 Development Estimates

7.4.1 Estimation Approach

The estimates below were obtained using expert opinion of documentation developers who had worked on similar systems.

7.4.2 Scope of Estimates

The estimates include interviews with developers, study of product documents, and review and inspection of output, as well as basic document preparation and revision. It is assumed that an eight-hour work day has five (5) effective hours in order to convert staff-hours to elapsed time.

7.4.3 Estimation Results

The development effort is summarized in the table below.

| Deliverable | Size | Duration | Effort |
| --- | --- | --- | --- |
| User’s Manual | 20 pages | 6 weeks | 1 person |
| Production |  | 1 week | Outsource |
| Error Manual | 10 pages | 3 weeks | 1 person |
| Production |  | 1 week | Outsource |
| “Help” screens | 30 menus | 9 weeks | 1 person |

The above refers to the document developer’s time only. An additional 180 staff-hours will be required from developers, etc., for review and inspection.

The actual production cost, based on 500 copies of two different manuals, and including covers, is estimated to be less than $5000.

7.4 Detailed Scheduling

The table following shows the final results of scheduling and staffing for the hardware portion of CCPS. The “task” level appears on the project task list.

| Deliverable Task Sub-Task | Supplier/Resp | Duration | Due Date | CWV | Actual Date |
| --- | --- | --- | --- | --- | --- |
| User’s Manual |  |  |  |  |  |
| Develop Prelim |  |  |  |  |  |
| Draft |  |  |  |  |  |
| Review |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Develop Final |  |  |  |  |  |
| Inspect |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Baseline, Reproduce, Distribute |  |  |  |  |  |
| Error Manual |  |  |  |  |  |
| Develop Prelim |  |  |  |  |  |
| Draft |  |  |  |  |  |
| Review |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Develop Final |  |  |  |  |  |
| Inspect |  |  |  |  |  |
| Revise |  |  |  |  |  |
| Baseline, Reproduce, Distribute |  |  |  |  |  |

| “Help” screens |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Design and review |  |  |  |  |  |
| Revise and Inspect |  |  |  |  |  |
| Baseline |  |  |  |  |  |

7.5 Document Delivery

Participants in the Beta site training course will be provided applicable documents. Further documents will be provided to the ATCO training organization. Each installed workstation will include applicable documents.

7.6 Document Standards

| Document (Type) | Standard |
| --- | --- |
| User Documents | MSDS Multi-weight Standard |
| Design Record Documents | MSDS Document Standards |
| Production Documents | N/A |
| Project Management Documents | Software Project Management Course |
| ATCO Contract | MSDS Contract Standards ATCO Contract Standards |
| Vendor Contract | MSDS Vendor Standards |

7.8 Budget and Resource Summary

| Discipline | Effort |
| --- | --- |
| Technical writer | 9 staff-weeks |
| Human Performance Engineer | 9 staff-weeks |

Document reproduction (binders, printing, etc.) costs should not exceed $5000.

Explanatory Notes

We have divided project deliverables into four classes, with corresponding special project plan sections, as shown below:

- User Documents

- Product Definition

- Hardware

- Software

There are more possible deliverables than these, e.g., the project plan itself. Cover the development of significant deliverables somewhere that makes sense, at a minimum, in the task list. If necessary, create a new plan section called, e.g., Project Deliverables.

This is not the only scheme possible, but is a reasonable one. You may find other needs, or not need some of these.

These documents are sometimes called “Design Record Documents.”

HPE - Human Performance Engineer (also Human Factors specialist). A person who knows how to design jobs, facilities, etc., for effective human performance, typically a psychologist.

Size of the deliverable in a reasonable unit, e.g., lines of code or feature points for software, gates or devices for hardware, lines or pages for documents. Always estimate the size and effort separately. The size is an inherent attribute of the product, given that a certain technology is chosen. The effort depends on how the job is done, for example, on the skill of the specific person doing the work.

The “task/sub-task” approach allows you to get to sufficient detail for accurate scheduling, but can keep the overall number of tracking items manageable at the project level. Tasks go on the project task list, but sub-tasks don’t.